## Sheet 1
Annexure 1
DRIFTSANDS/BLUE DOWNS - ITHEMBA
The acquisition of these properties is linked to the Department's catalytic project, namely the Southern Corridor Development Programme. One of the properties has been held by the Department for a number of years. It was acquired in 2001 for future human settlement purposes. The other properties are state owned and are targeted for purposes of expanding the development footprint on IThemba Farm. Again, the intention is to use these properties for decanting the informal settlements along the N2. The properties are located in close proximity to existing settlements and are considered well accessible due to the proximity of the N2 and Spine Road. Due to the scale of the project, the development will increase the thresholds that are able to support a great mix of economic opportunities and social amenities.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS OF LAND | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
19 |  | Erf 41965 - Blue Downs | 1.6435 | NDPW | Land owner yet to state asking price |  | Blue Downs | IThemba | DHS made request to NDPW | DHS has sent formal request for these properties to NDPW. Props Allocated to SAPS which must provide feedback by 31 March 2019 |  |  |  |  | 1 year | 10/11/2017 & 10/07/2018
20 |  | ST RE/Farm 981 | 131.7631 | NDPW | Land owner yet to state asking price |  | Blue Downs | IThemba | Request with formal proposal to be made to NDPW | [5 empty] | 1 year | 10/07/2018
|  | subtotal | 133.4066 | Price Subtotal | N/A
Delft TRA 5.1
The acquisition of these properties is linked to the Department's catalytic project, namely the Southern Corridor Development Programme. The required portion is fully encmbered by an informal settlement and a temporary relocation area which was built by this Department in the mid-2000's. The properties will be used for human settlement development purposes in order to upgrade the existing informal settlement. The property is located within an existing settlement which is Delft. It is considered that this property is well accessible due to the proximity of Symphony Way and Hindle Road which lead to Stellenbosch Arterial to the north and the R300 to the east. The development will further increase the thresholds that are required to support a mix of economic opportunities and social amenities in Delft.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE |  |  | LOCATION | Land Comment | STATUS |  |  |  |  | PRIORITY | DATE SENT
23 |  | A portion of Rem CA Farm 544 | 23.37 | NDPW | Land owner yet to state asking price |  |  | Delft | Request submitted to NDPW | Land acquisition request submitted to NDPW. DPW has confirmed to provide formal response a week after meeting on 1 April 2019. Last communication with Director for Land Disposals (Head Office) on 15/03/2019. |  |  |  |  | 1 year | 10/11/2017 & 22/05/2018 & 22/06/2018
|  | subtotal | 23.37 | Price Subtotal | N/A
WELTEVREDEN VALLEY - KOSOVO
The acquisition of these properties is linked to the Department's catalytic project, namely the Southern Corridor Development Programme. The majority of these properties are already encumbered by informal settlements which are targeted for upgrading and possible decanting to the wedge area. The identified properties will be used for human settlement development purposes in order to upgrade the existing Kosovo informal settlement. The properties are located within close proximity to existing settlements. It is considered that these properties are well accessible due to the proximity of the R300 which leads to the N2 to the east as well as the M7 to the west. The development will increase the thresholds that are required to support a mix of economic opportunities and social amenities in the Weltevreden and Philippi area.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS OF LAND | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
79 |  | A portion of CA-RE/Farm 1499 | 3.3866 | NDPW | Land owner yet to state asking price |  |  | Kosovo | Request submitted to NDPW | Land acquisition request submitted to NDPW. DHS met with SAPS in Feb 2019. SAPS to provide final response by 31 March 2019. |  |  |  |  | 1 year | 10/11/2017 & 22/052019 & 16/07/2019
|  | subtotal | 3.3866 | Price Subtotal | N/A
PROPERTIES FOR AFFORDABLE HOUSING WITHIN CITY OF CAPE TOWN
The Department gained access to a list containing 89 properties of which the ownership is disputed between National and Provincial Public Works. The Department undertook some assessment on the properties and has identfied that the below mentioned properties are better suited for human settlement purposes due to their extent, location, accessibility and potential housing yields. Many of the units are located within close proximity to nodal areas and are going to be utilised for affordable housing.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
194 |  | Erf 1061 - Bergvliet | 3.8708 | NDPW | N/A |  |  | Bergvliet | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | Affordable Housing | 2 year | 05/03/2018
195 |  | Erf 1274 - Camps Bay | 0.0874 | NDPW | N/A |  |  | Camps Bay | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. |  |  |  |  | Affordable Housing | 2 year | 05/03/2018
196 |  | Erf 1275 - Camps Bay | 0.0812 | NDPW | N/A |  |  | Camps Bay | [5 empty] | Affordable Housing | 2 year | 05/03/2018
197 |  | Erf 1276 - Camps Bay | 0.0812 | NDPW | N/A |  |  | Camps Bay | [5 empty] | Affordable Housing | 2 year | 05/03/2018
198 |  | Erf 1277 - Camps Bay | 0.0754 | NDPW | N/A |  |  | Camps Bay | [5 empty] | Affordable Housing | 2 year | 05/03/2018
199 |  | Erf 1278 - Camps Bay | 0.0754 | NDPW | N/A |  |  | Camps Bay | [5 empty] | Affordable Housing | 2 year | 05/03/2018
200 |  | Erf 1279 - Camps Bay | 0.0894 | NDPW | N/A |  |  | Camps Bay | [5 empty] | Affordable Housing | 2 year | 05/03/2018
214 |  | Erf 6350, Parow | 0.715 | NDPW | N/A |  |  | Parow | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. |  |  |  |  | Affordable Housing | 2 year | 10/11/2017 & 05/03/2018
215 |  | Erf 18625, Cape Town | 1.7337 | NDPW | N/A |  |  | Rugby | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. |  |  |  |  | Affordable Housing | 2 year | 10/11/2017 & 05/03/2018
216 |  | Erf 2120, Simons Town | 2.1846 | NDPW | N/A |  |  | Simons Town | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. |  |  |  |  | Affordable Housing | 2 year | 05/03/2018
217 |  | Erf 78053, Southfield | 0.7319 | NDPW | N/A |  |  | Southfield | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. | [5 empty] | 2 year | 05/03/2018
218 |  | Erf 1027, Tamboerskloof | 0.0605 | NDPW | N/A |  |  | Tamboerskloof | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. |  |  |  |  | Affordable Housing | 2 year | 05/03/2018
219 |  | Erf 279 - Zeekoevlei | 0.4104 | NDPW | N/A |  |  | Zeekoevlei | In progress. DPW confirmed vesting status to now lie with DTPW. DHS has requested confirmation of this from DTPW. | [5 empty] | 2 year | 10/11/2017 & 05/03/2018
220 |  | Erf 290 - Zeekoevlei | 2.4623 | NDPW | N/A |  |  | Zeekoevlei | [6 empty] | 2 year | 10/11/2017 & 05/03/2018
221 |  | Erf 872 - Zeekoevlei | 0.8164 | NDPW | N/A |  |  | Zeekoevlei | [6 empty] | 2 year | 10/11/2017 & 05/03/2018
222 |  | Erf 873 - Zeekoevlei | 0.2138 | NDPW | N/A |  |  | Zeekoevlei | [5 empty] | Affordable Housing | 2 year | 10/11/2017 & 05/03/2018
|  | Subtotal | 13.6894 | Price Subtotal | N/A
DRAKENSTEIN MUNICIPALITY
The Department of Human Settlements has been approached by the local authority which requests that the Department should assist in the assembly of land required for human settlement development purposes. The municipality has been encountering difficulty in acquiring the properties from state departments. Some of the properties have been pursued by the local authority for a significant period of time without positive feedback.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
223 |  | Erf 6411 - Paarl | 0.8614 | NDPW | Land owner yet to state asking price |  | Wellington (Caterville) | Drakenstein Municipality | The properties formed part of the Caterville Project that was completed a number of years ago. Currently the Department in conjunction with DM are investigating a few outstanding beneficiery complaints that could potentially lead to the construction of a small number of top structures if deemed necessary. The Caterville Project was a PHP project. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | UISP | 1 year | 11/12/2018
224 |  | Erf 6412 - Paarl | 2.68 | NDPW | Land owner yet to state asking price |  | Wellington (Caterville) | Drakenstein Municipality | [5 empty] | UISP | 1 year | 11/12/2018
|  | Subtotal | 3.5414 | Price Subtotal | N/A
THEEWATERSKLOOF MUNICIPALITY
The Department of Human Settlements has been approached by the local authority which requests that the Department should assist in the assembly of land required for human settlement development purposes. The municipality has been encountering difficulty in acquiring the properties from state departments. Some of the properties have been pursued by the local authority for a significant period of time without positive feedback, hence the request for this Department to intervene.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
231 |  | RE/Portion 1 of Farm 292, Caledon | 87.8915 | NDPW | N/A |  | Grabouw (Jagersvlakte) | TWK Municipality | Successfully acquired from DPW | Successfully acquired from DPW |  |  |  | UISP | acquisition complete | 05/03/2018
232 |  | Portion 4 of Farm 301, Caledon | 44.5638 | NDPW | N/A |  | Grabouw (Soopjevlake) | TWK Municipality | Successfully acquired from DPW | Successfully acquired from DPW |  |  |  | UISP | acquisition complete | 05/03/2018
234 |  | Farm 313/6, Caledon | 11.76 | NDPW | Land owner yet to state asking price |  | Grabouw Oderbrug (Hillside) | TWK Municipality | With head office for approval. DPW to enquire progress with head office and revert to DHS. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | UISP | 1 year | 22/05/2019 & 19/10/2019
235 |  | RE/Farm 295, Caledon | 385.4452 | NDPW | Land owner yet to state asking price |  | Grabouw | TWK Municipality | LM requested this land for economic development. |  |  |  |  | UISP | 1 year | 22/05/2019 & 18/10/2018
236 |  | Erf 4233, Grabouw | 129.5994 | NDPW | Land owner yet to state asking price |  | Grabouw | TWK Municipality | LM must clarify how much of this land is required for housing and other uses (traffic and cemetery). Land required for housing acan be donated to LM. LM must pay for land required for traffic department and cemetery. |  |  |  |  | UISP | 1 year | 05/03/2018 & 26/10/2018
237 |  | Erf 4237, Grabouw (consolidated for create Erf 4240 Grabouw) | 8.7037 | NDPW | Land owner yet to state asking price |  | Grabouw | TWK Municipality | This property matter has been forwarded to state attorney for transfer to the municipality. |  |  |  |  | UISP | 1 year | 05/03/2018
238 |  | Erf 611, Caledon | . | NDPW | Land owner yet to state asking price |  | Grabouw | TWK Municipality | This is a new request. However, DPW is aware of this request. |  |  |  |  | UISP | 1 year | 05/03/2018 & 18/10/2018
|  | Subtotal | 667.9636 | Price Subtotal | N/A
BREEDE VALLEY MUNICIPALITY
The Department of Human Settlements has been approached by the local authority which requests that the Department should assist in the assembly of land required for human settlement development purposes. The municipality has been encountering difficulty in acquiring the property from the said state department. The property has been pursued by the local authority for a significant period of time without positive feedback, hence the request for this Department to intervene.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
240 |  | Farm 82/65, Worcester | 40.3646 | NDPW | Land owner yet to state asking price |  | De Doorns (GG Kamp) | Breede Valley Municipality | DPW is willing to make available and it will be processed for release to the municipality. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | UISP | 1 year | 05/03/2018 & 19/09/2019
|  | Subtotal | 40.3646 | Price Subtotal | N/A
STELLENBOSCH MUNICIPALITY
The Department of Human Settlements has been approached by the local authority which requests that the Department should assist in the assembly of land required for human settlement development purposes. The municipality has been encountering difficulty in acquiring the properties from state departments. Some of the properties have been pursued by the local authority for a significant period of time without positive feedback, hence the request for this Department to intervene.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
241 |  | RE/Erf 64, Kylemore | 15.5245 | NDPW | Land owner yet to state asking price |  | Kylemore | Stellenbosch Municipality | Property must be transferred to municipality. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | UISP | 1 year | 05/03/2018 & 19/10/2018
242 |  | Erf 393, Stellenbosch | 0.0121 | NDPW | Land owner yet to state asking price |  | Vlottenburg Longlands | Stellenbosch Municipality | The ongoing negotiations between DPW and LM for the transfer of the land must be expedited. |  |  |  |  | UISP | 1 year | 05/03/2018 & 19/10/2018
243 |  | RE/Farm 1158, Paarl | 71.947 | NDPW | Land owner yet to state asking price |  | Franschhoek | Stellenbosch Municipality | LM recently identified new land parcels for the location of this project. Some of the pracels are located on DPW property and assistance is needed to transfer this property. |  |  |  |  | UISP | 1 year | 05/03/2018
244 |  | Farm 1618, Paarl | 164.5021 | NDPW | Land owner yet to state asking price |  | Franschhoek | Stellenbosch Municipality | [5 empty] | UISP | 1 year | 05/03/2018
245 |  | RE/Farm 1653, Paarl | 17.3991 | NDPW | Land owner yet to state asking price |  | Franschhoek | Stellenbosch Municipality | [5 empty] | UISP | 1 year | 05/03/2018
|  | Subtotal | 269.3848 | Price Subtotal | N/A
GEORGE LOCAL MUNICIPALITY
The Department of Human Settlements has been approached by the local authority which requests that the Department should assist in the assembly of land required for human settlement development purposes. The municipality has been encountering difficulty in acquiring the property from the said state department. The property has been pursued by the local authority for a significant period of time without positive feedback, hence the request for this Department to intervene.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
246 |  | Erf 329, George | 4.94 | NDPW | Land owner yet to state asking price |  | Wilderness Heights | George Mun | Assistance is needed to speed up the land acquisition. | DPW aware of request. DPW has informed DHS that it will provide formal response to requests via a letter that was due in 15 November 2018. New letter to be sent to DHS a week after meeting on 1 April 2019. |  |  |  | UISP | 1 year | 05/03/2018 & 08/02/2019
|  |  | 4.94 | Price Subtotal | N/A
BO-KAAP
Ministry was approached by residents from the Bo-Kaap area who reside in overcrowed households to address their need for adequate housing. A site inspection was conducted the investigate the various vacant land parcels identified by community members for possible housing development. Two sites were identified.
No | PLAN ANNOTATION | FARM/ERF | DEVELOPMENT AREA in HA | OWNERSHIP | PURCHASE PRICE | ADDRESS | SUBURB | LOCATION | Land Comment | STATUS | Reserved | Zoning and Land use | Reason for PoA | COMMENTS | PRIORITY | DATE SENT
261 |  | Erf 81, Tamboerskloof | 8.1 | NDPW | Land owner yet to state asking price |  |  | Bo-Kaap |  | (Erf 81)Request for acquisition was sent to NDPW, awaiting respone. (Ef 2967) Application for acquisition was submitted to CoCT who responded that the CoCT with the Dept's Affordable Housing section have earmarked the property for Social Housing. |  |  |  |  | 1 year | Year 2018
|  | Subtotal | 8.1 | Price Subtotal | N/A
|  | Total Extent | 1168.147 | Total Purchase Price | N/A | [9 empty] | 1 year - must be acquired within one year
2 year - must be acquired within two year
3 year - must be acquired within three year
outer - can be acquired in outer years