## Sheet1
Project No. | Service | Project Status | Total Expected Expenditure | Actual Expenditure to Date | Km completed since Commencement | Current FY Progress (% Complete)
C0749.02 | Upgrading of Main Road 191 (km 0.0 to km 9.57) and Periodic Maintenance of Main Road 191 (km 9.57 to km 41.95) | Approved and Contracted | 1016624975.31 | 498432658.98 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 49% Overall Completion
C0802.05 | Rehab MR533 between St Helena Bay (km 13,19) and Stompneus Bay (km 23,08) | Defects and liability period | 194493308.16 | 192611039.8 | The works have been completed in all respects Completion: 20250414 MR0553 (9,89 km) | Completed
C0838.06 | Rehab & Reseal of various sections on MR269 between Hemel-en-Aarde and Sandbaai, and Geometric improvements | Defects and liability period | 266503933.95 | 265039500.96 | The works have been completed in all respects Completion: 20241204 MR00269 (16 km) | Completed
C0838.08 | Repairs to Flood Damage Sections along MR269, between km 0,2 and km 1,85 | Approved and Contracted | 52085378.38 | 13582158.49 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 22% Overall Completion
C0851 | Upgrade DR1609 - Rondevlei | Defects and liability period | 114388306.2 | 112934013.69 | The works have been completed in all respects Completion: 20250627 DR01609 (6,4 km) DR01625 (0,3 km) | Completed
C0914 | Rehabilitation of MR168 between Annandale Road and Polkadraai | Defects and liability period | 331789360.08 | 328493379.11 | The works have been completed in all respects Completion: 20250828 DR01065 (0,23 km) MR00168 (20,52) OP05205 (0,42) | Completed
C0964.02 | Upgrade of TR33/1 at Beach Boulevard West (km 10.27) and Garret Street (km 13.05) | Approved and Contracted | 543343462.2 | 334603790.56 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 74% Overall Completion
C0967 | Malmesbury By-pass, Swartland | Approved and Contracted | 674033219.34 | 533688047.17 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 77% Overall Completion
C1000 | Upgrade of TR02802 between Stanford and Gansbaai | Defects and liability period | 491883960.77 | 489133136.63 | The works have been completed in all respects Completion: 20250609 OP04017 (4,4km) TR02802 (19,80km) | Completed
C1008 | Upgrade concrete road DR01688 between Calitzdorp Spa turnoff and Oudtshoorn | Defects and liability period | 248925742.98 | 249218505.85 | The works have been completed in all respects Completion: 20250519 DR01688 (27,67 km) | Completed
C1038.02 | Safety Improvement N7 Potsdam – Melkbos – Van Schoorsdrift I/C | Approved and Contracted | 776157949.87 | 396035742.31 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 55% Overall Completion
C1047.05 | The Completion of the widening of Bridge NO.2221 over Maalgate river | Approved and Contracted | 60195650.4 | 57912043.16 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 90% Overall Completion
C1049.03 | Upgrading of Divisional Road 1098 (km 5,47 to km 8,79) and Rehabilitation of Divisional Road 1098 (km 8,79 to km 14,24). | Approved and Contracted | 145966381.44 | 127650372.2 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 89% Overall Completion
C1102.01 | The Upgrade of Main Road 201 (R301) between the N1 (Paarl) and OP5255 (Kliprug Road) | Approved and Contracted | 215503239.11 | 205014125.73 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 90% Overall Completion
C1105.01 | Periodic Maintenance Of Trunk Road TR00902 – Du Toitskloof Pass from km 0.21 to km 21.25 | Approved and Contracted | 167540883.74 | 103412884.66 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 77% Overall Completion
C1116.01 | The Periodic Maintenance of TR22/1 (km 20.60 to km 36.05), TR22/2 (km 3.55 to km 71.8) and MR316 (km 0.0 TO km 0.25) from Wolseley to Touwsrivier | Defects and liability period | 165104416.15 | 160425618.9 | The works have been completed in all respects Completion: 20250228 MR00316 (0,25km) TR02201 (83, 25km) | Completed
C1125 | Periodic Maintenance of TR83/1, TR83/2 and MR365 - Riversdale to Ladismith | Defects and liability period | 177665900.7 | 172202992.36 | The works have been completed in all respects Completion: 20250310 TR08301 (17,72 km) TR08302 (18,92 km) MR00365 (14,12 km) TR03105 (0,48 km) | Completed
C1141 | PeriodicMaintenane of TR03103,MR295,MR00294,DR01356 AND OP06046 - MONTAGU | Defects and liability period | 114938217.16 | 113948747.93 | The works have been completed in all respects Completion: 20250227 DR01356 (4,41) MR00294 (1,59 km) MR00295 (55km) OP06046 (2,47 km) TR03103 (31,78) | Completed
C1142 | The Upgrade of DR1099 The Strengthening of MR205 and the Periodic Maintenance Of MR189, DR1090 and OP5215 near Klapmuts | Approved and Contracted | 231545259.62 | 160463851.42 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 63% Overall Completion
C1145 | Periodic Maintenance of DR01123, TR02501 and MR00174 - Drakenstein Municipality | Defects and liability period | 95329793.15 | 92338332.09 | The works have been completed in all respects Completion: 20250228 DR01123 (6,95 km) MR00174 (14,91 km) TR02501 (4,01 km) DR01123 (5,3 km) | Completed
C1146 | Periodic Maintenance of MR00351, MR00355, DR01615, DR01600 and DR01627 - Knysna | Defects and liability period | 112632570.18 | 112632570.19 | The works have been completed in all respects Completion: 20250328 DR01600 (6,89 km) DR01615 (2,61 km) DR01627 (8 km) MR00351 (17,67 km) MR00355 (16,76 km | Completed
C1147 | Periodic Maintenance of MR00552, MR00546, DR02220 - Lutzville | Retention | 81327283.86 | 80177283.88 | The works have been completed in all respects Completion: 20240717 Final Approval: 20250717 DR02220 (3,57 km) MR00546 (17,09 km) MR00552 (24,28 km) | Completed
C1154 | The Periodic Maintenance of TR33/2, MR344, DR1582 and OP6811 near Hartenbos | Defects and liability period | 117347919.93 | 116197919.91 | The works have been completed in all respects Completion: 20250224 DR01582 (1,29 km) MR00344 (1,55 km) OP06811 (0,48 km) TR03302 (50 km) | Completed
C1158.02 | Replacement of Bridge B0495, and Emergency Flood Damage Repait of Bridges B6150 and B5983 near De Doorns | Defects and liability period | 86333834.53 | 79212128.91 | The works have been completed in all respects Completion: 20250923 | Completed
C1203.01 | Periodic Maintenance of TR30/2, TR31/1, DR1347, DR1379, DR1400 and DR1377 near Worcester | Approved and Contracted | 202562344.47 | 91614876.01 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 30% Overall Completion
C1205 | The Periodic Maintenance of MR00291 | Defects and liability period | 74746091.77 | 73208389.6 | The works have been completed in all respects Completion: 20250508 MR00289 (5 km) MR00291 (9,72 km) DR01363 (2,84 km) DR01358 (4,05 km) DR01365 (2,80 km) | Completed
C1213 | The Periodic Maintenance of TR16/8 & TR16/9 between Northern Cape Border and Murraysburg | Defects and liability period | 98507590.36 | 97352200.41 | The works have been completed in all respects Completion: 20241213 TR01609 (41,42 km) TR01608 (4,6 km) | Completed
C1214 | Periodic Maintenance of MR00331 between Still Bay and Groot-Jongensfontein | Completed | 25491107.27 | 25491107.29 | The works have been completed in all respects Completion: 20240530 Final Approval: 20250604 MR00331 (9,14 km) | Completed
C1216 | The Periodic Maintenance of MR310, DR1458 and DR1487 between Ceres and Op Die Berg | Approved and Contracted | 709712371.97 | 461638287.69 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 66% Overall Completion
C1230 | The Periodic Maintenance of TR85/1,TR21/2,MR559 and OP7643 within the Saldanha Bay Area | Defects and liability period | 82197906.66 | 82197906.6 | The works have been completed in all respects Completion: 20250213 OP07643 (2,52 km) MR00559 (9,55 km) TR02102 (12,05 km) TR08501 (3,62 km) | Completed
C1270.01 | Emergency Flood Damage Repairs: Miller’s Point Slope Failure | Defects and liability period | 32385183.15 | 30099732.63 | The works have been completed in all respects Completion: 20250303 MR00101 (0,15 km) | Completed
C1270.02 | Emergency Damage Repairs to Riviersonderend Bridge B0562 on DR1279 at km 20.96 | Defects and liability period | 12884163.84 | 12562059.75 | The works have been completed in all respects Completion: 20250314 | Completed
C1270.03 | Emergency Repairs to Elandsdrift Bridge B1388 on DR1205: km 50.84 | Defects and liability period | 11568645.2 | 11433952.95 | The works have been completed in all respects Completion: 20250702 | Completed
C1270.04 | Emergency Repairs on Clarence Drive (TR02701) | Defects and liability period | 79830565.94 | 78335565.94 | The works have been completed in all respects Completion: 20250704 TR02701 (73 km) | Completed
C1270.05 | Emergency Flood Damage Repairs to Hartbeesrivier Causeway C12405 on OP04096 at km 1.14 | Approved and Contracted | 49120416.86 | 45195857.92 | The works have been completed in all respects Completion: 20251025 | Completed
C1270.09 | Emergency Flood Damage Repairs to DR1325, DR1354 and OP6072 in the Barrydale Area | Approved and Contracted | 6440000 | 0 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | Construction is ongoing
C1271.03 | Emergency Flood Damage Repair of DR1254 and DR1271 | Defects and liability period | 39278945.08 | 39278945.07 | The works have been completed in all respects Completion: 20241212 | Completed
C1271.04 | The Emergency Flood Damage Repair On Various Roads In The Villiersdorp Area | Defects and liability period | 45049489.94 | 45049489.95 | The works have been completed in all respects Completion: 20250304 OP05662 (1,18 km) OP5671 (0,95 km) MR00279 (20,53 km) DR01285 (10,17km) OP1300 (2,99 km) OP4060 (0,7 km) DR01347 (25,64 km) DR01320 (9,5 km) | Completed
C1271.05 | Emergency Flood Damage Repair Of Various Roads In The Grabouw Area | Defects and liability period | 47185460.53 | 46804940.95 | The works have been completed in all respects Completion: 20250131 TR03001 (2 km) DR01288 (20,30 km) | Completed
C1271.08 | Emergency Flood Damage Repair In the Helderstroom and Greyton Area | Completed | 3479534.95 | 3479534.96 | The works have been completed in all respects Completion: 20240807 Final Approval: 20250818 DR01313 (0,6 km) | Completed
C1271.09 | Emergency Flood Damage Repair In the Robertson and Montagu Areas | Defects and liability period | 27271961.92 | 26590162.87 | The works have been completed in all respects Completion: 20250312 TR03102 (2 km) TR03103 (0,1 km) OP06042 (0,9 km) | Completed
C1271.10 | Emergency Flood Damage Repair In The Worcester Area II | Defects and liability period | 26092365.18 | 25567062.02 | The works have been completed in all respects Completion: 20250730 | Completed
C1271.11 | Flood Damage Repairs on TR30/2, MR279 and DR1336 - Villiersdorp Area | Approved and Contracted | 31659069.2 | 8753407.08 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 47% Overall Completion
C1308 | Repair of Uitkyk Pass (DR1487) In the Cederberg Wilderness Area | Defects and liability period | 67516841.41 | 64518945.5 | The works have been completed in all respects Completion: 20250523 DR01487 (10,44 km) | Completed
C1315 | Emergency Repairs of MR276 - Boontjieskraal | Defects and liability period | 44263470.92 | 42921428.49 | The works have been completed in all respects Completion: 20250827 MR00276 (6,04 km) | Completed
C1317 | Flood Damage Repairs on DR1223, DR1227, OP4170, OP4171 and OP4430 - Overberg | Defects and liability period | 16309492.58 | 14627391.65 | The works have been completed in all respects Completion: 20251031 OP04430 (5,72 km) | Completed
C1318.01 | Flood Damage Repairs on DR1308 and DR1309 - Greyton | Approved and Contracted | 18321651.08 | 6460281.62 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 43% Overall Completion
C1318.02 | Flood Damage Repairs on OP4040, OP4041 and OP4044 - Baardskeerdersbos | Approved and Contracted | 24192172.63 | 9485835.37 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 45% Overall Completion
C1321.01 | Flood Damage Repairs along DR1577 and OP4548 near Riversdale and DRl433, DRl 710, OP6454 and OP6496 near Ladismith | Approved and Contracted | 55792324.12 | 13325653.57 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 45% Overall Completion
C1321.02 | Flood Damage Repairs Along TR75/2 and Dr1713 near Oudtshoorn | Approved and Contracted | 61648548.12 | 8848448.58 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 90% Overall Completion
C1319 | Flood Damage Repairs on DR1347, DR1395, DR1423, OP5662, OP5663 and OP6074 – Breede Valley | Approved and Contracted | 30572645.52 | 9694441.53 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 41% Overall Completion
C1322.01 | Flood Damage Repairs Along DR1649 near Volmoed | Approved and Contracted | 59052083.67 | 7460480.11 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 60% Overall Completion
C1322.02 | Flood Damage Repairs along DR1703, DR1704, MR368, DR1843 near De Rust and Uniondale | Approved and Contracted | 50237757.49 | 9121264.8 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 75% Overall Completion
C1101 | Strengthening of TR1/1 km 0,0 to km 0,6 between George and Oudtshoorn | Approved and Contracted | 193949999.93 | 0 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | Construction is ongoing
C1157.02 | Flood Damage Repairs on MR355 (Seven Passes), DR1602, DR1633, DR1639 and DR1791 | Approved and Contracted | 60459229.27 | 0 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | Construction is ongoing
C1215 | The Periodic Maintenance of DR1770, DR1775, DR1782 and OP7202: Plettenberg Bay | Approved and Contracted | 46662671.33 | 4424873.56 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | 11% Overall Completion
C1270.11 | Emergency Flood Damage Repairs to Overpass Bridge B5796 Along TR08101 at km 9.76 in the Weltevreden Area | Approved and Contracted | 4208123.43 | 0 | Construction is ongoing, completion of individual sections of road (kms) only documented at practical completion of the project. | Construction is ongoing